## Tabelle1
| Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
10 | Scalability | application breaks / is irresponsive with growing user base | 7 | 9 | 63 | layer architecture / docker | Denis
8 | Insufficent time estimation | tasks take longer than estimated and time schedule breaks | 7 | 7 | 49 | multiple person estimation / function points / time buffer | Denis
11 | Obsessing over details | team focuses on unimportant details instead of progressing the whole project | 7 | 7 | 49 | regular meetings and reevaluation of scope | Inga
7 | Ineffective collaboration | teammembers do not communicate properly or get into fights | 5 | 9 | 45 | team meetings, documentation and retros | Celina
2 | Code quality | bad coding slows or breaks the application | 4 | 8 | 32 | Code reviews | Inga
4 | Late changes to requirements | the customer wants last minute changes to scope or functionalities | 4 | 7 | 28 | scrum based project manangement | Celina
6 | Local build fails | framework build fails on individual computer | 8 | 2 | 16 | gradle wrapper | Nils / comes with Android
1 | Failing deployment | the attempt to deploy new features fails | 2 | 7 | 14 | CICD pipeline | Nils
3 | Illness / hardware breakdown | a teammember falls ill for a longer period or used hardware breaks | 2 | 2 | 4 | git repository | Celina
9 | Security | wip gets attacked from the outside | 1 | 3 | 3 | use encoding / no actual data | Inga
5 | Breaking changes in technology | Technology updates deprecate current code | 2 | 1 | 2 | use stable software | Denis